PART 1 - GENERAL

1.1	SUMMARY

A.	This Section specifies administrative and procedural requirements, in addition to those defined in the General Conditions for GC/CM Projects at the University of Washington, for schedule software, Baseline Progress Schedule preparation, monthly Progress Schedule updates, contemporaneous period schedule analysis, submittal schedules, and short interval schedules.

B.	Related Sections:

- 01 26 00, “Contract Modification Procedures”

- 01 29 76, “Progress Payment Procedures”

- 01 50 00, “Temporary Facilities and Controls”

- 01 77 00, “Closeout Procedures”

C.	Owner’s forms included by reference for this Section include (see Appendix A):

- Short Interval Schedule

- Contemporaneous Period Schedule Analysis

D.	As used in this Section, “Progress Schedule” refers collectively to “Baseline Progress Schedule” and “monthly Progress Schedule updates”.

1.2	SCHEDULE SOFTWARE

A.	The Contractor shall provide Owner an authorized copy, including all original manuals, of the latest version of Primavera Project Management® for Windows or an alternate Owner approved computer scheduling software with equivalent functionality.  The selected software must be capable of performing baseline-to-current schedule comparisons, cost and resource loading functions, and have the option of executing scheduling calculations in either "retained logic" or "progress override" mode.  Activities must be able to process lead and lag time relationships, start-to-start or finish-to-finish relationships, and be capable of being "hammocked" as required.  The software must be registered to the Owner and be provided in Windows format and on CD format compatible with the Owner's computer.

B.	If Primavera Project Management® is not used by the Contractor, the Contractor shall provide training and continuing service at the Contractor's cost to Owner’s personnel in the use of the selected software.

C.	Total Float is defined as the amount of time between the earliest start date and the latest start date, or between the earliest finish date and the latest finish date of an activity on the Progress Schedule.  Float is not for the exclusive use of either the Contractor or the Owner unless otherwise identified in the Contract Documents.

1.	Extensions of time for Contract performance will be granted only to the extent that equitable time adjustments to the affected activity or activities exceed the total float time along the affected paths of the current Progress Schedule at the time a Field Order, or Change Order, was issued for the change.

D.	All Progress Schedule submittals, including monthly Progress Schedule updates, will be reviewed jointly by the Owner's Representative and the Contractor.  Such review of the Contractor's schedules shall not constitute an approval or acceptance of the Contractor's construction means, methods, or sequencing or its ability to complete the Work in a timely manner.

1.3	PROGRESS SCHEDULE

A.	Within sixty (60) calendar days after GC/CM Contract execution, the Contractor shall prepare and submit to the Owner, for review and comment, a preliminary Progress Schedule utilizing a Critical Path Method (CPM) logic, based on the Contract Documents.  The Owner will review the preliminary schedule for conformance with the Contract Documents and provide comments within fourteen (14) calendar days of receipt from the Contractor.  The Contractor shall respond to all comments and provide the Owner a Baseline Progress Schedule within fourteen (14) calendar days of receipt of the Owner’s comments.

B.	Once the Baseline Progress Schedule is submitted to the Owner, the Progress Schedule shall be formally established as the baseline file within the Contractor’s scheduling software.  This baseline file shall not be modified without the Owner’s written approval.

- The amount specified in Section 01 29 76 shall be withheld from the Contractor's monthly Application for Payment if the Baseline Progress Schedule is past due.

C.	The Baseline Progress Schedule shall be the basis that the Contractor shall used: plan, organize, and execute the Work; record and report actual performance and progress through updates, and; show how the Contractor plans to complete all remaining Work.  The Baseline Progress Schedule and monthly Progress Schedule updates shall be the basis for consideration and analysis of requests for time extensions as specified below.  The schedule shall be in the form of an activity oriented precedence network diagram.

D.	The Baseline Progress Schedule and monthly Progress Schedule updates shall be constructed to show the order in which the Contractor proposes to carry out the Work and to indicate the restrictions of access to and availability of work area, and availability and use of manpower, materials, equipment, and include all activities of trade contractors, equipment vendors, suppliers, and Negotiated Support Services expenses.  The Progress Schedule shall incorporate contractually specified limitations and restrictions, and contractually specified milestones.  Construction activities shall match or be correlated with the pay items in the approved Schedule of Values.  The Progress Schedule shall be prepared in sufficient detail with the assignment and coding of all activities by the Contractor and Subcontractors in consideration of, but not limited to, the following Work activities:

- Access and availability to the Project Site, including road closures;

- Interfaces and dependencies with preceding, concurrent, and succeeding contractors, if applicable;

- The type of work to be performed and labor trades involved;

- All procurement, manufacturing, fabrication (both on-site and off-site), and delivery activities for all major materials and equipment;

- Shutdowns of existing Owner’s equipment and utility services;

- Required delivery dates of OFCI equipment and materials;

- Testing, air balancing, and commissioning activities, including submission and approval of test results and final commissioning report;

- Approvals required by regulatory agencies or other third parties, including obtaining an Occupancy Permit;

- Coordination for Owner’s occupancy including Owner’s cleaning, OFOI equipment and furnishings installations;

- Planning for phased occupancy by the Owner, with intermediate completion dates;

- Contractor’s preliminary cleaning and final cleaning operations;

- Contractor’s Final Punch List Report, Owner’s Final Inspection (Punch List), Contractor’s corrections, and Owner’s re-inspection;

- Substantial Completion and Final Completion activities and milestones, and Final Acceptance.

E.	The activities defined in the Progress Schedule shall represent the planned durations in anticipation of normal man-power and equipment utilization in durations of whole working days.  No activity durations shall exceed twenty two (22) working days.  If approved by the Owner, longer durations may be allowed for non-construction activities such as procurement, delivery, or submittal activities.  All durations shall be determined based upon resource planning under contractually defined on-site work conditions.  In calculating activity durations, normal inclement weather shall be considered.  The Contractor shall schedule the Work to minimize the effect of adverse weather.  The Contractor shall also protect the work site from the effects of adverse weather or take other necessary measures such that the Work can be completed within the time established in the Contract Documents and include these provisions in the schedule as appropriate.

F.	Schedule activity identification codes shall not be alphanumeric unless approved by Owner.

- Activity Description:  Provide adequate information to readily identify each activity up to 48 characters in the general descriptive format:  action, item, location (such as Install Steel Studs 3rd Floor).

- Activity Codes:  The Contractor shall develop and provide a complete, efficient and understandable Work Breakdown Structure (WBS) code to submit to the Owner for review and approval.  In addition to the WBS, activity codes may be created and assigned a conventional WBS scheme, activity codes shall be used in lieu of the WBS. Suggested character fields for the code structure are:

| Name | Length | Description |
| --- | --- | --- |
| PHAS | 1 | Phase or stage |
| TYPE | 4 | Type of activity |
| FLOR | 1 | Floor |
| AREA | 4 | Area and/or room |
| RESP | 7 | Responsible party |
| SPEC | 5 | CSI section number |
| OF/CI | 4 | Owner Furnished/Contractor Installed Equipment |

- The Critical Path shall be clearly indicated on all diagrams submitted.  An activity is critical when it is part of the longest duration pathway(s) through the CPM network or when its total float is less than or equal to zero.

- At the Owner's request, furnish a written narrative of the Contractor's determination of durations for particular activities.  Such explanation may include the number of crews, crew composition, number of shifts per day, number of hours in a shift, and number of work days per week, construction equipment, material quantities, productivity qualifiers (such as weather), etc.

- At the Owner's request, a written explanation shall be provided for leads and/or lags on relationships and for constrained dates.  These scheduling constraints shall be disallowed unless a compelling reason exists for their use.

- Clearly identify activities which are planned to use of overtime, double shifts, work on weekends or holidays.

- Schedule Statistics Report:  Each submittal involving graphical and/or tabular reports using CPM shall be accompanied by a Schedule Statistics Report.  Include a listing of activities with open ends and out-of-sequence progress, constraints, the schedule calculation modes (retained; contiguous or interruptible) and other statistics that are normally a part of this report.

G.	Activities shall be cost-loaded.  The estimated costs to perform each Work activity shall be assigned to each activity included in the network as specified by the scheduling software.  The sum of the costs assigned to all activities shall equal the Total Contract Cost in the approved Schedule of Values.  No activity costs shall be assigned to manufacturing or delivery activities unless approved by the Owner.  Using the cost assigned to each activity, develop a cash flow projection demonstrating the estimated cash draw down by month over the period of the Project.  The cash flow projection shall be illustrated by a graphic display as generated by the computer scheduling software.

- Contractor shall provide Owner with a formula to convert cost loaded activities to manpower requirements.  This formula shall be based upon a percentage allocation of the cost loading for labor costs and an average hourly labor cost for the Project.

- The total cost of each Subcontractor's construction activities in the Final Schedule of Values "Total Contract Cost" shall be equal to the total Subcontractor's Contract Sum amount, (see Section 01 29 76 "Progress Payment Procedures").

- Contractor may request and Owner may approve, at its sole discretion, an alternative resource-loading plan if it is evaluated equally beneficial.

H.	Tabular reports required by this Section shall be prepared by the scheduling software.  Reports shall contain a listing of the activities as required for the type of report being prepared.  Each activity shall include the following information:

- Activity ID;

- Activity Description;

- Original and remaining durations in work days;

- Early start and finish dates;

- Actual start and finish dates (as applicable for monthly update reports);

- Late start and finish dates;

- Total float in work days;

- Percentage of activity completed;

- The budgeted cost, if cost-loaded;

- Assigned activity codes;

- Predecessor and successor activity numbers;

- Leads/Lags on activity relationships;

- Activities with constraints, and;

- Reportable milestone activities, as agreed with Owner.

I.	The Contractor shall prepare computer generated tabular reports as part of the initial schedule submission and for each monthly update thereafter as follows:

- A list of the “nearly critical’ (Total Float is equal to or less than 5 days) activities, sorted by activity number with predecessor and successor relationships;

2.	The Short Interval Schedule.

3.	Other reports that the Owner and Contractor may negotiate as the Project evolves.

J.	The Contractor shall submit the Progress Schedule consisting of the reports and diagrams as specified by this Section monthly, in the following quantities.

- One copy of a Primavera Project Management® (or approved equal) generated detailed network diagram displaying all activities in a time scaled format with their logical relationships.  The network need not be confined to a single sheet but shall be printed on either C or D drawing size.

- One copy of the Primavera Project Management® (or approved equal) updated project file in its native format on a CD compatible with the Owner's computer.

K.	Qualifications:  The Contractor shall submit the resume(s) of the designated person(s) responsible for schedules and reports (the "Contractor's Scheduler"), who is not the Project Manager or Superintendant.  The "Contractor's Scheduler" shall have demonstrable capability to plan, coordinate, execute, and monitor a CPM schedule as required for this Project.  Submit the qualifications of the "Contractor's Scheduler" no later than five (5) days after the GC/CM Contract execution.  The Owner's Representative will approve or reasonably disapprove the proposed "Contractor's Scheduler".  In the event of disapproval; a new scheduler shall be proposed within one (1) week and be subject to the same consideration criteria as noted above.

L.	Certification:  When requested by the Owner, submit certification that each Subcontractor and major equipment supplier has participated in, reviewed, and concurs with the Progress Schedule and the associated cost data as it relates to their Work.

1.4	MONTHLY PROGRESS SCHEDULE UPDATES

A.	The Contractor is required to prepare and submit monthly Progress Schedule updates and to participate in monthly schedule update meetings with the Owner as described below.

- Timely submission of updates is of significant and crucial importance to the management of the Project.  Lack of, or late receipt of, updates diminishes their value to the Owner.  If a monthly Progress Schedule update is not submitted to and reviewed with the Owner prior to the Contractor submitting its monthly Application for Payment; the monthly Schedule of Values amount for Progress Schedule updates may, at the Owner’s sole judgment and discretion, be reduced from the Specified General Conditions by a unilateral Change Order (see Section 01 29 76, "Progress Payment Procedures").

B.	The Contractor shall prepare monthly Progress Schedule updates to reflect work progress achieved since the previous update.  Historical performance data and/or records shall not be changed without approval of the Owner.

C.	The Contractor shall, in a second and subsequent report, incorporate any logic and duration changes that represent its revised planning, provided all such changes are identified and submitted to the Owner for comment in the narrative report required herein this Section.

D.	The Contractor shall use and maintain a fixed end date when generating the required reports and diagrams for the Owner as specified by this Section.  The fixed end date shall be the Substantial Completion date.  The fixed end date will be adjusted in subsequent updates only to reflect approved time extensions incorporated by Change Order.

E.	The Project shall be rescheduled each reporting period with:

- An updated data date.

- Actual start/finish dates.

- Percent complete.

- Remaining durations (for each activity in the “status” or “current file).

F.	Show changes occurring since the previous schedule submission, such as:

- Any major changes in scope.

- Activities modified since previous submission including, but not limited to, logic changes.

- Revised projections for progress and completion, as applicable.

- Any other identifiable changes.

G.	The Contractor shall account for all rain days, for major events, and similar excusable non-compensable delays, during which little or no work is progressed and that are acknowledged by the Owner, in the period within which the events occur.  The Contractor may account for such delays within the Contemporaneous Period Schedule Analysis and the Progress Schedule update by treating the events as it would a typical holiday at the calendar function of the software.  By whatever method the Contractor chooses to account for such delays and events, a narrative description of the accounting shall be included with the narrative report required herein this Section.

H.	The Construction Progress Meeting shall be held prior to the Owner’s review and comment of the Contractor’s monthly draft Application for Payment, unless otherwise approved by Owner.

1.	The Contractor shall provide copies of two tabular reports:

  - A total float report clearly indicating the current critical path through Substantial Completion.

  - A report of activities sorted by early start dates commencing with the previous monthly progress update and including all updated activities during the previous month.  Actual progress of the previous month will be recorded and incorporated into the update.

2.	The Contractor shall provide copies of a narrative report to include:

- A description of the Work that has progressed.

- An explanation of the Work that had been scheduled to be performed in the previous period but as not performed, and why is was not performed.

- Anticipated delay and impact on schedule.

- Corrective action recommended and its effect.

- A discussion of the Work scheduled for the upcoming period noting any issues or events that could impact this work.

- If the Contractor intends to make logic or original activity duration change(s), the report will include such changes.  To facilitate Owner's review the Contractor will provide a "Claimdigger" report which indicates all proposed changes to the schedule.

3.	The Contractor and Owner shall review these reports and discuss any differences or issues raised.

1.5	CONTEMPORANEOUS PERIOD SCHEDULE ANALYSIS

A.	It is the Owner's desire and intent to resolve all issues affecting the Substantial Completion date in a timely, efficient, and effective manner.  To achieve this goal, the Owner and Contractor shall participate in contemporaneous analyses of all delays and advances of the schedule by application of the Contemporaneous Period Schedule Analysis method.  The Contemporaneous Period Schedule Analysis shall coincide with the monthly schedule update meetings.

- Format for the Contemporaneous Period Schedule Analysis should be similar to the Owner’s form.

B.	Assessment of impacts due to changes or other events, in accordance with the Contemporaneous Period Schedule Analysis method described herein, must be performed on the most recent update of the Progress Schedule.  Further, impacts due to changes or other events shall be assessed utilizing the Progress Schedule update that represents the data date closest to, and just prior to, the date of the impacting event.  An alternative method can be to progress the schedule to a data date that represents the date of the impacting event.  Subsequent to the assessment of schedule sequences representing the impacting events, the schedule may be updated to the next data date with appropriate logic or duration changes resulting from the impacting events.  All data shall be provided to the Owner.

C.	The logic and planning elements of the Progress Schedule are the Contractor’s responsibility.

- No Contract Time shall be modified unless directed by an approved Change Order.

D.	Submission of a valid monthly Progress Schedule update and the completion of the Contemporaneous Period Schedule Analysis are conditions precedent to the review and approval of any request for an extension in the Contract Time.  Failure to complete monthly Progress Schedule updates and to participate in Contemporaneous Period Schedule Analysis will defer consideration of any time extensions by the Owner until the Work is completed and all as-built progress can be analyzed by the Owner.  Further, the Owner will assess liquidated damages, if any, regardless of the status of any requests for time extensions pending, until any such requests are resolved.

E.	The Contractor shall obtain training by a qualified consultant in the application of the Contemporaneous Period Schedule Analysis method.  The training shall be provided to appropriate Contractor field personnel, appropriate major Subcontractor personnel, and appropriate Owner personnel.  The training should not exceed one day.  The requirement for training may be waived by the Owner provided the Contractor can demonstrate sufficient working knowledge of the Contemporaneous Period Schedule Analysis method.  The Contractor shall bear all costs for training specified herein.

1.6	SUBMITTAL SCHEDULE

A.	General:  Within ten (10) calendar days following the Owner’s receipt of the Baseline Progress Schedule, the Contractor shall prepare and submit to the Owner a complete schedule of work related submittals based on the Progress Schedule, as required by the Contract Documents (“Submittal Schedule”).  Correlate Submittal Schedule with the listing of principal Subcontractors.

- The amount specified in Section 01 29 76 shall be withheld from the Contractor's monthly Application for Payment if the Submittal Schedule, referenced in 1.6 of this Section, is past due.

B.	Form:  Prepare Submittal Schedule in chronological sequence of submittals.  Show category of submittal, name of Subcontractor, generic description of work covered, related Specification Section numbers, activity or event code on the Progress Schedule baseline file, scheduled date for first submission, and blank columns for actual date of submittal, re-submittal, and final release or acceptance by the A/E.  The Submittal Schedule shall be prepared in sufficient detail and in consideration of, but not limited to, the following:

- Preparation and submission of shop drawings, layout drawings, product data, material samples, and mock-ups.

C.	Update the Submittal Schedule monthly and submit to Owner.

1.7	SHORT INTERVAL SCHEDULE

A.   	Short Interval Schedule:  Prepare and update weekly a four (4) week Short Interval Schedule. Show previous week of actual progress (planned vs. actual performance).  Forecast three (3) weeks of start and completion dates for each activity, task or event in comparison to the Progress Schedule.

1.	Activities in the Short Interval Schedule shall relate directly to activities in the Progress Schedule.

B.	Format for the Short Interval Schedule should be similar to the Owner’s form. This format is reproducible from the available Primavera Project Management® report formats; however, the Contractor may submit an alternative format that must first be approved by the Owner.  The format shall include comment annotation as necessary.

C.	Copies of the Short Interval Schedule shall be provided at the Construction Progress Meetings and will be used as a basis for discussion of progress and planned work at the meetings.

PART 2 - PRODUCTS (Not Used)

PARK 3 - EXECUTION (Not Used)

END OF SECTION