## PDG Projects List
UW FACILITIES, PROJECT DELIVERY GROUP |  |  |  |  | ACTIVE CONSTRUCTION PROJECTS | [7 empty] | 2026-09-01
|  |  |  | BUILDER'S RISK APPLICABLE (YES OR NO) |  | MINI BUILDER'S RISK POLICY (YES OR NO) |  |  |  | CONST MANAGER |  |  |  |  | CONTRACTUAL DATE OF | ACTUAL
| 207906 | PROJECT NAME | FACNUM |  | BUILDING |  | CONTRACTOR | CONTRACT | CONTRACT |  | PROJECT | CONTRACT | ARCHITECT/ | NOTICE TO | SUBSTANTIAL | SUBSTANTIAL
[5 empty] | TYPE |  |  | TYPE | AMOUNT |  | MANAGER | ADMINISTRATOR | ENGINEER | PROCEED | COMPLETION | COMPLETION
ACTIVE DBB CONSTRUCTION PROJECTS
| 207607 | MV Switch andTransformer Replacement North Campus | 3750 | Yes | NC | Yes | Colvico Inc | DBB | 708688 | Dillon | Harrison | Marriott | Studio Meng S | 2023-09-14 | 2026-03-09
| 207608 | Medium Voltage Renewal South Campus | 3750 | Yes | NC | Yes | Prime Electric | DBB | 1281900 | Babinec | Harrison | Marriott | Studio Meng S | 2024-02-12 | 2025-09-02
| 207840 | UWMC Facilities Mechanical Upgrades | 1254 | Yes | FR | Yes | BNBuilders, Inc. | CPCR | 2269405 | Babinec | Mathews | Marriott | Hargis Engineers | 2022-08-10 | 2023-07-21 | 2025-01-28
| 207875 | SOD D1 Simulation Clinic Renovation and Expansion | 1328 | Yes | NC | Yes | Andersen Construction | DBB | 882900 | Babinec | Mathews | Paxton | Buffalo Design | 2025-04-02 | 2025-09-19 | 2025-09-30
| 207921 | UWMC Rad/Onc Vault C Equipment Replacement | 4541 | Yes | NC | Yes | BNBuilders, Inc. | CPCR | 2238915 | Olson | Mathews | Paxton | Jamieson | 2025-02-13 | 2026-02-03
| 207999 | UWMC NW Wish Remodel Easy Street | 6450 | Yes | NC | Yes | Bayley Construction | CPCR | 2326929 | Ericson | Szygorski | Paxton | Jamieson | 2024-07-15 | 2024-12-27 | 2025-02-02
| 208048 | Fleet Charging Stations & Security, N26 | 1148, 3863 | No | NC | Yes | Colvico Inc | DBB | 1368688 | Dillon | Severns | Robinson | Reid Middleton | 2024-08-05 | 2025-03-18 | 2025-12-30
| 208049 | Fleet Charging Stations & Security, E02 | 3741 | No | NC | Yes | Anvil Builders | DBB | 3760254 | Dillon | Severns | Robinson | Reid Middleton | 2026-07-10 | 2027-11-22
| 208054 | CPG Safety and Security Improvements | 1133 | Yes | NC | Yes | GLY Construction | DBB | 2134407 | Dillon | Severns | Paxton | McGranahan | 2023-11-15 | 2024-06-27 | 2024-12-19
| 208077 | UWMC NW A-Wing 2nd IR Lab and CPU Perioperative Bays | 6446 | Yes | NC | Yes | GLY | CPCR | 3131479 | Ericson | Szygorski | Paxton | NBBJ | 2024-05-28 | 2025-05-19 | 2025-10-06
| 208159 | MHSC B&D Wing Dental Water | 1304 | Yes | NC | Yes | JTM Construction | DBB | 1900000 | Olson | Mathews | Robinson | SSW | 2024-03-26 | 2024-11-05 | 2025-12-22
| 208232 | Anechoic Chamber Installation |  | Yes | NC | Yes | Reynolds GC | DBB | 1942000 | Olson | Sirois | Marriott | Miller Hull | 2024-12-05 | 2025-05-09 | 2025-08-29
| 208250 | S1 Short Term/Intermed. Maint. Improvements | 1295 | Yes | NC | Yes | Contech Services | DBB | 2013811 | Hosseini/Dillon | Distler | Robinson | Stemper | 2026-06-02 | 2026-09-25
| 208298 | Emergency Transformer Replacement Wilcox | 1345 | Yes | NA | Yes | GLY Construction | EMR | 307117 | Dufel | Harrison | Paxton | Hargis Engineers | 2023-07-19 | ASAP
| 208349 | Transformer & Swtichgear Replacement 23-25 | 3750 | Yes | NC | Yes | Colvico Inc | DBB | 1218600 | Dillon | Mengher | Robinson | Studio Meng S | 2024-11-04 | 2026-02-20
| 208444 | Miller Hall Technology Hub | 1192 | Yes | NC | Yes | JTM Construction | DBB | 387351 | Olsen | Contreras | Robinson | SHKS | 2025-06-02 | 2025-11-17 | 2026-04-30
* | 208453 | UW Tower Elevator Modernization | 4593 | Yes | NC | Yes | CDK Construction | DBB | 5855000 | Hosseini | Contreras | Marriott | Greenbusch | 2026-08-17 | 2029-01-08
| 208475 | Nano ES G061A Microscope Room Modification | 6428 | Yes | NA | Yes | GLY Construction | DBB | 670787 | Brown | Reynolds | Paxton | Miller Hull | 2026-05-18 | 2026-11-16
| 208480 | UMC Elevators 212,213,214, Modernize | 1256/1255 | Yes | NA | Yes | Abbott Construction | CPCR | 3585000 | Olson | Mathews | Paxton | ZGF | 2025-04-30 | 2027-07-19
| 208484 | BB Tower Elevator Security | 1223 | Yes | NC | Yes | GLY Construction | DBB | 1042395 | Ikemoto | Reynolds | Brewer | McGranahan | 2024-08-19 | 2025-02-10
| 208488 | ADA Pathways Remediation State Project |  | No | NC | Yes | Sunset Grill Construction | DBB | 1771545.95 | Olsen | Simon | Robinson | KPFF | 2025-04-18 | 2025-08-25
| 208489 | HMC 1WH-422 CT Scanner Room Upgrade | 4346 | Yes | NC | Yes | Aldrich + Associates Inc | DBB | 698000 | Spaulding | Gilge | Robinson | Jamieson | 2024-12-30 | 2025-03-25 | 2025-04-22
| 208525 | UWMC ML Rapid Treatment & Administration | 1255 | Yes | NC | Yes | BNBuilders, Inc. | CPCR | 1389769 | Gilge | Ikemoto | Brewer | Ankrom | 2025-04-04 | 2026-03-12 | 2026-03-09
| 208552 | Allen School Data Center Completion | 6502 | Yes | NC | Yes | Apex Mechanical | DBB | 527000 | Dillon | Reynolds | Brewer | Miller Hull | 2025-07-25 | 2026-02-17
| 208559 | UW Bothell IAS Media Production Studio | 6354 | Yes | NC | Yes | Andersen Construction | DBB | 380950 | Babinec | Stone | Marriott | McGranahan | 2025-10-27 | 2025-03-16
| 208562 | CCW Piping Extension in Tunnel | 3774 | Yes | NC | Yes | Shinn Mechanical | DBB | 3495632 | Brown | Harrison | Robinson | AEI | 2026-04-06 | 2026-11-04
| 208570 | Kane Hall CAAMS Upgrades | 1276 | Yes | NA | Yes | GLY Construction | DBB | 1471952 | Babinec | Reynolds | Paxton | SHKS | 2026-06-08 | 2026-11-16
| 208584 | Visitor Locker Room - Hec Ed | 1195 | Yes | NC | Yes | LBC Construction | DBB | 775100 | Brown | Scrapper | Robinson | Gensler | 2026-05-05 | 2026-07-31
| 208600 | Chemistry Building Replace Process Chillers | 1108 | Yes | NA | Yes | Apex Mechanical | DBB | 699000 | Wojcicki | Severns | Paxton | SHKS | 2026-06-29 | 2027-02-24
| 208609 | UWMC ML NW PCCT Upgrades | 6091 | Yes | NC | Yes | Abbott Construction | CPCR | 1368819 | Olsen | Gilge | Brewer | Ankrom | 2026-07-16 | 2027-01-02
| 208649 | Husky Soccer - FIFA Field Renovation | 1861 | Yes | NC | Yes | Premier Field Development | DBB | 2245906.11 | Dillon | Mathews | Marriott | DA Hogan | 2025-05-30 | 2025-08-01 | 2025-08-07
| 208683 | ADA Parking Conset Decree Phase 3.3 | 1861 | No | NA | Yes | Always Active Services | DBB | 1057000 | Dufel | Simon | Brewer | KPFF | 2026-04-21 | 2026-06-22
| 208687 | UWMC ML TRU Pathology Lab/7S Soiled | 1259 | Yes | NA | Yes | JTM Construction | CPCR | 464674 | Brown | Gilge | Paxton | ZGF | 2026-05-22 | 2026-10-12
| 208688 | UWT Emergency Power Repairs | 4539 | No | NA | No | Abbott Construction | EMR | 2066098 | Ikemoto | Contreras | Paxton | Hargis Engineers | 2024-07-18 | 2026-05-20
| 208670 | UWMC NW E-Wing HVAC Addition to 6 Rooms | 6450 | Yes | NC | Yes | GLY Construction | DBB | 1240750 | Ericson | Szygorski | Brewer | Ankrom | 2025-10-09 | 2026-06-01
| 208717 | NW Cath Lab Equipment Replacement | 6446 | Yes | NC | Yes | Sellen Construction | DBB | 1155566 | Huard | Szygorski | Marriott | ZGF | 2025-12-19 | 2026-09-19 | 2026-06-12
| 208721 | UWMC ML CT Procedural Equipment Upgrade | 4541 | Yes | NA | Yes | Aldrich + Associates Inc | CPCR | 1026000 | Ikemoto | Zhang | Paxton | Ankrom | 2026-01-08 | 2026-08-04
| 208738 | HMC 1WH Angio Remodel | 4346 | Yes | NC | Yes | GLY Construction | DBB | 1450000 | Ericson | Gilge | Brewer | Clark/Kjos Architects | 2025-04-07 | 2025-09-24 | 2026-10-24
| 208773 | CREST/CAMP - New 3D Printing Suite | 1168 | Yes | NA | Yes | JTM Construction | DBB | 1311000 | Wojcicki | Reynolds | Marriott | SHKS | 2026-05-21 | 2026-10-19
| 208795 | UWB LB2 Reuse - Core Campus Student Services | 4054 | Yes | NC | Yes | Reynolds GC | DBB | 1774625 | Hosseini | Stone | Brewer | KPFF | 2026-04-20 | 2026-11-03
* | 208839 | UWMC ML NORA Therapeutic 1&2 Booms | 4541 | Yes | NC | Yes | DPR Construction | DBB | 666500 | Spaulding | Zhang | Marriott | SRG | 2026-07-20 | 2026-11-23
* | 208857 | FA Panel Upgrades Phase 2 | 1314 | Yes | NC | Yes | Andersen Construction | DBB | 2490000 | Wojcicki | Contreras | Marriott | NA | 2026-07-07 | 2027-10-31
| 209038 | UWMC NW B-Wing Re-Roof | 6447 | Yes | NC | Yes | Lease Crutcher Lewis | DBB | 4574066 | Olson | Terao | Brewer | SHKS | 2026-06-01 | 2027-07-06
| 209232 | McCarty Hall Concrete Collapse | 1158 | Yes | NA | Yes | GLY Construction | EMR | 58259 | Wojcicki | Kennedy | Paxton | TBD | 2026-06-16 | TBD
| 209232 | McCarty Hall Concrete Collapse | 1158 | Yes | NA | Yes | Andersen Construction | EMR | 422676 | Wojcicki | Kennedy | Paxton | TBD | 2026-06-26 | TBD
| 45 | project(s) |  |  |  |  | 73606514.06
ESCO PROJECTS
| 208548 | CPBPS Infra Struct Ren-Energy Studies VFD |  | Yes | NC | Yes | ATS Automation | ESCO | 49800 | Dillon | Mengher | Marriott | NA | 2025-01-17
| 208549 | CBPS Infra Struct Ren-Energy Chiller | 4595 | Yes | NC | Yes | McKinstry Company | ESCO | 164600 | Olsen | Mengher | Marriott | NA | 2025-01-17 | 2027-03-02
| 208661 | CBPS Infra Struc Ren-Energy VFD Suzzallo | 1193 | Yes | NA | Yes | ATS Automation | ESCO | 1197377 | Olsen | Mengher | Paxton | NA | 2025-01-17 | 2026-12-31
| 208804 | Uw Bothell Chiller & Cooling Towers Replacement | 4016 | Yes | NA | Yes | ATS Automation | ESCO | 3588887 | Hosseini | Mengher | Paxton | NA | 2025-12-26 | 2027-02-22
| 208876 | UWB EHW Electrification | 4526 | Yes | NA | Yes | McKinstry Company | ESCO | 96200 | Hosseini | Mengher | Marriott | NA | 2026-02-25 | In Process
| 209046 | UWMC OPMC Cooling Tower Replacement | 6423 | Yes | NC | Yes | MacDonald-Miller | ESCO | 1558353 | Huard | Mengher | Brewer | NA | 2026-01-15 | 2026-07-22
| 6 | project(s) |  |  |  |  | 6655217
JOB ORDER CONTRACTS - GLY & BNBuilders CONSTRUCTION
| 207239 | UWMC ML Secondary Water Disinfection | 1257/1260/1261/1222/1223 | Yes | NC | Yes | GLY Construction | JOC | 94807 | Spaulding | Mathews | Brewer | Harris | 2026-05-08 | 2026-07-30
| 208077 | UWMC NW A Wings 1st Floor and ED Shower | 6446 | Yes | NC | Yes | GLY Construction | JOC | 397402 | Szygorski | Ericson | Paxton | NBBJ | 2024-03-06 | 2024-06-25 | 2024-11-06
| 208446 | Marine Studies Space Renovation | 1122 | Yes | NC | Yes | GLY Construction | JOC | 241922 | Reynolds | Brown | Brewer | Gensler | 2026-02-12 | 2026-06-05
| 208704 | Coast Salish Story Pole Installation | 1181 | No | NC | Yes | GLY Construction | JOC | 191670 | Wojcicki | Simon | Brewer | KPFF | 2025-06-19 | 2025-08-27
| 208745 | DJC Bar Renovation | 1188 | Yes | NC | Yes | GLY Construction | JOC | 428823 | Dillon | Mathews | Brewer | Gensler | 2025-06-13 | 2025-08-29 | 2025-12-31
| 208785 | Husky Stadium Football Hydrotheraphy Pool Reno |  | Yes | NC | Yes | GLY Construction | JOC | 429917 | Dillon | Mathews | Robinson | Gensler | 2025-06-02 | 2025-08-28 | 2025-08-31
| 208840 | HMC 5MB Toilet Replacement | 5992 | Yes | NC | Yes | BNBuilders, Inc. | JOC | 451229 | Gilge | Spalding | Brewer | NA | 2026-03-23 | 2026-10-30
| 209110 | Glenn Hughes Penthouse Theatre Carpet | 1209 | Yes | NC | Yes | BNBuilders, Inc. | JOC | 237471.44 | Brown | Contreras | Brewer | NA | 2026-03-24 | 2026-06-30
| 209151 | McMahon Phase 1 | 1143 | Yes | NC | Yes | BNBuilders, Inc. | JOC | 366183 | Brown | Ruegamer | Marriott | Lund Opsahl | 2026-05-26 | 2026-09-01
| 209160 | SOM HSB F510 Nbio Shefin Lab | 1226 | YES | NC | Yes | GLY Construction | JOC | 262156 | Wojcicki | Contreras | Brewer | NA | 2026-05-11 | 2026-09-15
* | 209168 | HMCGCT - 44 | 6128 | Yes | NC | Yes | GLY Construction | JOC | 257461 | Spaulding | Gilge | Paxton | NA | 2026-07-21 | 2026-09-30
| 10 | project(s) |  |  |  |  | 3101580.44
MAJOR PROJECTS - GCCM /DB
| 203203 | Anderson Hall Renovation | 1351 | No | NC | No | Lease Crutcher Lewis | DB | 27442384 | Olsen | Sirois | Marriott | Hennebery | 2024-09-18 | 2026-01-29 | 2026-01-23
| 205611 | MHSC T Wing Renovation | 1168 | Yes | NC | No | Skanska USA Building, Inc. | DB | 44039806 | Olson | Sirois | Paxton | Miller Hull | 2024-03-29 | 2025-12-31
| 206756 | ASUW Shell House Restoration | 1187 | Yes | WF | No | Sellen Construction | DB | 11676249 | Dillon | Scraper | Marriott | Mithun | 2025-07-16 | 2026-08-20
| 206874 | Chemical Sciences Building | 1206, 1279 | Yes | NA | No | Skanska USA Building, Inc | IDB | 151425 | Olsen | Sirois | Robinson | TBD | 2024-09-24 | TBD
| 206829 | ICA Basketball Training/Operations Center | 1196 | Yes | NC | No | Mortenson Construction | IDB | 44320000 | Dillon | Scraper | Robinson | Gensler | 2024-03-04 | 2025-08-22 | 2025-09-19
| 206927 | Behavioral Health Teaching Facility |  | Yes | NC | No | Clark+Abbott JV | IDB | 169343595 | Ericson | Natta | Paxton | SRG | 2021-07-15 | 2023-09-28 | 2024-01-31
| 207313 | Haggett Hall Replacement |  | Yes |  | No | Andersen Construction | IDB | 153291620 | Wojcicki | Stone | Robinson | Mahlum | 2024-10-23 | 2027-04-30
| 207507 | UWMC Montlake Membrane & Landscape Replacement | 1259, 1258, 1257, 1256, 1223 | Yes | NC | No | Skanska | DB | 36358318 | Ikemoto | Natta | Paxton | LMN | 2022-10-05 | 2025-08-13 | 2025-12-23
| 207653 | UWMC NW Behavioral Health Renovation | 6314 | Yes | NC | No | BNBuilders | DB | 9402204 | Ericson | Young | Robinson | KMD | 2023-12-27 | 2025-01-10 | 2025-04-28
| 207852 | UWMC NW A-Wing 4-5 Floors Renovation | 6446 | Yes | NC | No | GLY Construction | DBB | 12017445 | Ericson | Young | Marriott | Ankrom Moisan | 2025-04-17 | 2027-07-19 | 2026-05-19
| 207956 | UWMC NW B Wing Roof Mechanical | 6447 | Yes | NC | No | Abbott Construction | DB | 11715787 | Ericson | Szygorski | Marriott | Stemper | 2025-06-30 | 2026-03-06
| 207979 | UWMC ML Kitchen Cafeteria Expansion Renovation | 1256 | Yes | NC | No | Abbott Construction | DB | 50000 | Ericson | Sezgin | Marriott | ZGF | Preliminary Agreement | TBD
| 207986 | UWMC NW OPMC D.H. Procedure & Clinic | 6423 | Yes | NC | No | Abbott Construction | DB | 10766834 | Ericson | Szygorski | Marriott | NBBJ | 2024-12-19 | 2025-10-27 | 2025-12-30
| 208055 | Burke Gilman Trail Transit Access, Safety Efficiency Improvements | 6293 | Yes | NA | No | Granite | DB | 85125 | TBD | Simon | Paxton | KPFF | Preliminary Agreement | TBD
| 208120 | UWMC ML 9NE/SE/Chil/Atrium /3NE/SE R | 4541 | Yes | NA | No | Abbott Construction | DB | 9388605 | Dufel | Mathews | Paxton | Evolution | 2023-07-18 | 2024-08-30 | 2025-06-23
| 208176 | HMC NJB ORs Sleep Clinic Relocate | 6017, 4358 | Yes | NC | No | Mortenson | DB | 22272902 | Glass | Sezgin | Robinson | Perkins+Will | 2024-06-14 | 2025-10-01 | 2025-09-29
| 208573 | Seismic Phase 5 | 1193, 1195, 1298 | Yes | NA | No | GLY | GCCM | 13207495 | Wojcicki | Contreras | Paxton | Bassetti | 2025-06-16 | 2028-06-30
| 208557 | Big Ten Broadcast Control Center |  | Yes | NC | No | GLY Construction | DB | 9823256 | Dillon | Scraper | Marriott | HLW | 2025-07-23 | 2026-04-26 | 2026-05-14
* | 208563 | Centralized Cooling Building Connects | 1314 | Yes | NC | No | Andersen Construction | DB | 5966609 | Brown | Mengher | Marriott | Auburn Mech. P2S | 2026-06-16 | 2027-05-27
| 208606 | UWMC NW MOB Gamma Knife | 6422 | Yes | NC | No | Mortenson Construction | DB | 5026558 | Ericson | Young | Marriott | Perkins + Will | 2024-12-05 | 2025-05-16 | 2025-07-10
| 208657 | Art and Music Renovation: Phase 2 -Music Building | 1299 | Yes | NA | No | Mortenson | GCCM | 5756517 | Wojcicki | Simon | Paxton | LMN | 2026-04-28 | 2027-03-31
| 208758 | UW Lab Medicine Roche Automation Upgrade | 1259 | Yes | NC | No | BNBuilders | DB | 16495582 | Ikemoto | Young | Paxton | PKA | 2026-02-24 | 2027-03-25
| 208772 | Welcome Center |  | Yes | NC | No | Lease Crutcher Lewis | IDB | 17140322 | Wojcicki | Distler | Paxton | Studio Tsien | Desgin/ Preconstruction Phase
| 208799 | UW Tacoma Energy Upgrades Project Portfolio | 4539100040456410 | Yes | NA | No | Mortenson | DB | 6025608 | Ikemoto | Mengher | Paxton | BCE | 2026-04-29 | 2027-09-02
| 208817 | UWMC ML Energy Efficiency Upgrades | 1259 | Yes | NC | No | Abbott Construction | GCCM | 205610 | Spaulding | Mengher | Marriott | AEI | Preconstruction Agreement | TBD
| 209022 | MHSC BB Wing Elev. & Transformers Replace | 1223 | Yes | NC | No | Sellen Construction | DB | 50000 | Hosseini | Contreras | Marriott | ZGF | Preliminary Agreement | TBD
| 25 | project(s) |  |  |  |  | 642019856
TOTALS
| 88 | projects |  |  |  |  | 725640628.5 | [7 empty] | Revised: | 2026-09-02
| CC= | Construction Contract Under $90K |  |  |  |  | SWR= | Small Works Roster |  |  | WF= |  | Wood Frame Building
| EMR= | Emergency |  |  |  |  | JOC= | Job Order Contract |  |  | JM= |  | Joisted Masonry Const.
| DBB= | Design Bid Build |  |  |  |  | CPCR = | Critical Patient Care Roster |  |  | NC= |  | Non-Combustible
| DB= | Design Build | [8 empty] | FR= |  | Fire Resistive
| GCCM = | General Contractor/Construction Manager |  |  |  |  | *= | New project this report |  |  | NA= |  | Non-applicable
| ESCO= | Energy Savings Construction Contract
Please email Shelly Marriott to request changes to this information or distribution. (smarriot@uw.edu)