ATTACHMENT C

DOCUMENT REVIEW PROCESS

This Document Review Process outlines those steps which relate to the processes of document reviews required by the Owner.  Participants shall include the A/E and its sub-consultants, the UW Facilities Project Delivery Group Project Manager (UW Project Manager), and other Owner representatives, including the Project’s client, Owner’s consultants, Environmental Health and Safety (EH&S), UW Information Technology (UW-IT), Campus Engineering, and Facilities Services, as appropriate.  All comments will be submitted and resolved on the Owner’s REVIEW COMMENT RESOLUTION FORM, Attachment E.

PART I - PRELIMINARY DESIGN PHASE

The Document Review Process begins during the Preliminary Design Phase.  Review meetings are anticipated to require one (1) day for each meeting at this Phase.

1.	Project Kick-off Meeting:

- Attendance shall include:  the A/E, all A/E sub-consultants, UW Project Manager and other Owner representatives, as appropriate.

- The UW Project Manager will:  introduce the Project team members; review the Project scope, schedule, and Maximum Allowable Construction Cost (MACC), and; review the application of the University Design Guides.

- The A/E shall:  review codes, laws and policies affecting the Project; review details of the Project, identifying affected features and systems and issues to be addressed; review Attachment B deliverables; schedule the over-the-shoulder review meetings for the Phase, and; prepare and distribute meeting minutes documenting the meeting discussion to all attendees within two (2) working days of the meeting.

2.	Intermediate Phase Review Meeting:

The A/E and its sub-consultants shall make presentations to the Owner’s representatives to explain the developing design.  Discussions shall be convened by discipline, approximating the headings of Attachment B, for a detailed review of the information.  The A/E shall provide a list of exceptions, if any, to the Project’s program requirements entitled Exception to Project Requirements List for Owner’s approval.  The meeting shall include time for discussion, questions, and answers.  All clarifications and resolutions of Project issues and features shall be recorded in minutes of each discussion prepared and distributed by the A/E to the attendees within two (2) working days of the meeting.  Meeting minutes shall identify persons responsible for action items and due dates, and include the Exception to Project Requirements List.

A set of in-progress Preliminary Design Phase documents shall be available at the meeting.

3.	Owner’s Final Phase Review:

Upon receipt of the final Preliminary Design Phase documents, Owner’s reviewers will evaluate aspects of the Project relevant to their discipline.  Reviewers will prepare written comments for submittal to the UW Project Manager prior to the announced deadline.

Comments, Responses, and Resolution:

- The UW Project Manager will receive, clarify, and edit duplicate review comments in consultation with the reviewers and submit the comments to the A/E for response prior to the Review Comments Resolution Meeting.

- The UW Project Manager will review the A/E’s written responses to ensure that the resolution is clear and appropriate for the Phase, distribute the A/E’s written responses to reviewers and request sign-off of the responses and/or notification of unresolved comments by the Review Comments Resolution Meeting.  Unresolved comments will be identified to the Architect for discussion and resolution at the Review Comments Resolution Meeting.  Comments that are accepted by the Owner for future resolution shall be documented by the A/E in an unresolved review comments list for resolution during the Construction Documents Phase.

4.	Review Comments Resolution Meeting:

Purpose:

Prior to approval of the Preliminary Design Phase a determination will be made by the Owner that the documents are complete based upon the Project’s program requirements and the requirements of Attachment B for the Phase.  If the Owner determines that the documents are incomplete the A/E shall continue working toward completion until the documents are acceptable.

Process:

The A/E and its sub-consultants shall make presentations to the Owner’s representatives to describe the final Design Phase documents and to explain the detail of individual components of the work and the reasons for the particular solution.  Discussions shall be convened by discipline, approximating the headings of Attachment B, for a detailed review of the information.  The A/E shall update the Exception to Project Requirements List identifying new items for Owner’s approval, if any, including any exceptions to the requirements of Attachment B for the Phase.  The meeting shall include time for discussion, questions, and answers.  Open action items shall be reviewed.  All clarifications and resolutions of Project issues and features shall be recorded in minutes of each discussion prepared and distributed by the A/E to the attendees within two (2) working days of the meeting.  Meeting minutes shall identify unresolved action items from previous meetings and new action items identifying persons responsible for resolution and due dates, and include the Exception to Project Requirements List and the unresolved review comments list, if any.

A set of final Preliminary Design Phase documents shall be present at the meeting.

5.	Project’s Client Review Meeting:

The A/E shall meet with the Owner’s Project client to describe the functional detail of the Preliminary Design Phase documents, and to document the Project client’s approval of the Preliminary Design Phase submittal.  This meeting may be included as part of the Review Comments Resolution Meeting, at the Owner’s discretion.

6.   	Other Meetings: Indicated by (

(	Board of Regents

- Architectural Commission

(	University Landscape Advisory Committee

(	University Standing Committee on Accessibility

(	CUCAC

When the Preliminary Design Phase documents are approved, the UW Project Manager will send notice to the A/E of such approval, subject to any written actions, modifications, or additional design information which shall be provided by the Architect during the Construction Documents Phase.

PART II - CONSTRUCTION DOCUMENTS PHASE

Review meetings are anticipated to require one (1) day for each meeting at this Phase.  Meetings required due to the Owner’s written Preliminary Design Phase approval requirements are in addition to review meetings.

7.	Intermediate Phase Review Meeting:

There shall be at least one intermediate review meeting during the Construction Documents Phase which maybe at the time of permit submittal, if approved by the Owner.

The A/E and its sub-consultants shall make presentations to the Owner’s representatives to describe the developing Construction Documents.  Discussions shall be convened by discipline, approximating the headings of Attachment B, for a detailed review of the information.  The A/E shall update the Exception to Project Requirements List identifying new items for Owner’s approval, if any.  The meeting shall include time for discussion, questions, and answers.  Open action items and unresolved Preliminary Design Phase review comments shall be discussed and resolved.  All clarifications and resolutions of Project issues and features shall be recorded in minutes of each discussion prepared and distributed by the A/E to the attendees within two (2) working days of the meeting.  Meeting minutes shall identify unresolved action items from previous meetings and new action items identifying persons responsible for resolution and due dates, and include the Exception to Project Requirements List, if any.

A set of in-progress Construction Documents shall be present at the meeting.

8.	Final Review:

Upon receipt of the final Construction Documents, Owner’s reviewers will evaluate aspects of the Project relevant to their discipline.  Reviewers will prepare written comments for submittal to the UW Project Manager prior to the announced deadline.

Comments, Responses, and Resolution

- The UW Project Manager will receive, clarify, and edit duplicate review comments and comments requesting new requirements in consultation with the reviewers and submit the comments to the A/E for response prior to the Acceptance Review Meeting.

- The UW Project Manager will review the A/E’s written responses to ensure that the resolution is clear and appropriate for the Phase, distribute the A/E’s written responses to reviewers and request sign-off of the responses and/or notification of unresolved comments by the Acceptance Review Meeting.  Unresolved comments will be identified to the A/E for discussion and resolution at the Acceptance Review Meeting.

- If unresolved comments remain after the Acceptance Review Meeting the A/E shall continue to work to provide solutions acceptable to the Owner that shall be reviewed with the Owner for sign-off, allowing time for Contractor bidding, unless otherwise agreed by Owner.

9.	Acceptance Panel Review Meeting:

Purpose:

Prior to approval of the Construction Documents Phase a determination will be made by the Owner that the documents are acceptable for bidding.

Process:

The A/E and its sub-consultants shall make presentations to the Owner’s representatives to explain the Construction Documents and to demonstrate compliance with the Project’s program requirements, the approved Design Phase documents, and the Owner’s review comments.  Discussions shall be convened by discipline, approximating the headings of Attachment B, for a detailed review of the information.  The meeting shall include time for discussion, questions, and answers.  All previous meeting minutes action items shall be resolved and the resolutions shall be recorded in minutes of each discussion prepared and distributed by the A/E to the attendees within two (2) working days of the meeting.

A set of final Construction Documents shall be present at the meeting.

When the Construction Documents are approved for the Bidding Phase, the UW Project Manager shall send written notice to the A/E of such approval, subject to any written actions or required addenda modifications.

End of Attachment C