PART 1 - GENERAL

  - SUMMARY

- This Section includes the administrative and procedural requirements for Design-Builder progress payment and release of retainage as herein specified.

- Owner’s forms referenced in this Section include (see Appendix A):

- Application and Certificate for Payment on Contract (Application for Payment)

- Construction Invoice Voucher

- Retainage Invoice Voucher

- Monthly Specialty Consultant/Specialty Trade Contractor List and Certifications

- Statement of Intent to Pay Prevailing Wages and Affidavit of Wages Paid Information

- Certificate of Payment of Labor and Materials

- Apprentice and Journey Level Worker Utilization Report

- Monthly Safety Report

  - PREREQUISITES FOR FIRST APPLICATION FOR PAYMENT

A.	Prevailing Wage Forms:  Submit Statement of Intent to Pay Prevailing Wages form, approved by the Department of Labor and Industries, prior to commencing the Work.  The Owner will not make payment on an Application for Payment until the Design-Builder has an approved Intent on file with the Department of Labor and Industries for the Design-Builder and every Specialty Trade Contractor of every tier that performed work during the payment period and are included in an Application for Payment.  The form shall list every classification of laborer, worker, or mechanic employed by the Design-Builder and its Specialty Trade Contractors.  THERE ARE NO EXCEPTIONS TO THIS REQUIREMENT.

- Prevailing Wage forms, and Prevailing Wage Rates, can be obtained directly from the Department of Labor and Industries website. https://lni.wa.gov/licensing-permits/public-works-projects/contractors-employers/.

B.	Schedule of Values:  Submit and receive approval of the Schedule of Values in accordance with this section and Article 7 of the Agreement. Before submitting the first Application for Payment, submit and receive approval of the Schedule of Values allocating the detail of the Guaranteed Maximum Price, in a breakdown acceptable to the Owner, which shall be documented on the G703 Application for Payment.  The approved Schedule of Values will (i) subdivide the Work into its respective parts, and (ii) serve as the basis for monthly progress payments made to Design-Builder throughout the Work.  PAYMENT FOR WORK WILL ONLY BE MADE FOR, AND IN ACCORDANCE WITH, THOSE ITEMS INCLUDED IN THE APPROVED SCHEDULE OF VALUES. ADJUSTMENTS TO THE APPROVED SCHEDULE OF VALUES CAN BE MADE ON A MONTHLY BASIS, OR AS AGREED TO BY THE OWNER, AND DOCUMENTED ON THE G703.

- Format:  G703

2.  	Round figures to nearest dollar amount.

3.	Make sum of total Costs equal to the Guaranteed Maximum Price. Do not include State of Washington sales tax.

4.	Coordinate items of the Schedule of Values so that there is a corresponding item in the Progress Schedule.

5.	Revise as requested by Owner.

C.	Specialty Trade Contractors List:  Submit a list of all Specialty Trade Contractors and major material suppliers.

D.	Retainage:  Submit instructions for the disposition of retainage funds.

1.	In accordance with Chapter 60.28 RCW, Owner shall reserve a Contract retainage in an amount not-to-exceed 5% of the moneys earned by the Design-Builder as a trust fund for the protection and payment of:

- The claims of any person arising under the Contract Documents;

- The State of Washington with respect to taxes imposed pursuant to Titles 50, 51, and 82 RCW which may be due from the Design-Builder, and;

c.	The Owner for claims it may have against the Design-Builder.

2.	Design-Builder's written instructions should be addressed to the University of Washington, Project Delivery Group, Accounting Department, Box 352205, Seattle, Washington 98195 - 2205.

3.	At the option of the Design-Builder, the moneys reserved by the Owner shall be:

- Retained in a fund by the Owner; or

- Bonded by the Design-Builder (if approved by Owner) for all of the Contract retainage in a form acceptable to the Owner; or

- Deposited by the Owner in an Owner’s interest bearing account in a bank, mutual savings bank, or savings and loan association; or

d.	Placed in escrow with a bank or trust company by the Owner.

(1)	Escrow Agent:  If the retained funds are to be placed in escrow, Design-Builder will select the escrow agent, subject to approval by the Owner.  The selected agent must be a bank or trust company in the State of Washington.

(2)	Escrow Agreement:  Pursuant to electing the escrow option, an escrow agreement shall be executed by Design-Builder, Owner, and bank.  A completed and signed escrow agreement in a form acceptable to the Owner must be on file with the Owner for payment before the Design-Builder's first Application for Payment is processed.

(3)	Escrow Payments:  As each progress estimate is presented for payment, Design-Builder shall make a voucher request for the retained funds that are to be placed in escrow.  Such requests should be prepared on the Owner’s Retainage Invoice Voucher form and submitted in four (4) copies with the related Application for Payment.  Upon receiving a retainage invoice, the Owner will issue a check payable to the Design-Builder and the bank jointly.  Such checks will be mailed to the bank and the Design-Builder will receive copies of check transmittal letters.

(4)	Escrow Investments:  The bank shall invest the retained funds in bonds and other securities selected by the Design-Builder from the following list approved by the Owner:

- Bills, certificates, notes or bonds of the United States;

- Other obligations of the United States or its agencies;

- Obligations of any corporation wholly owned by the government of the United States;

- Indebtedness of the Federal National Mortgage Association;

- Time deposits in commercial banks, mutual savings banks, and savings and loan associations in the State of Washington;

(f)	Deposits in savings accounts in commercial banks, mutual savings banks, and savings and loan associations in the State of Washington.

(5)	The investments selected must mature on or prior to the date set for Substantial Completion, including extensions thereof or no later than forty five (45) days following the Final Acceptance of the Work.  Interest on such investments shall be paid to the Design-Builder by the escrow agent as it accrues.

(6)	Escrow Costs and Fees:  All escrow costs and fees shall be paid by the Design-Builder, in accordance with the escrow agreement.

  - DRAFT APPLICATION FOR PAYMENT

A.	On or about the twenty-fifth (25th) of each month, the Design-Builder shall submit to the Owner a draft Application for Payment for the Work properly performed during the current calendar month in accordance with this section and Article 7 of the Agreement.  Include projected costs to the end of the month in the pay request.  Provide the following documents (draft documents may be marked by hand):

- Application and Certificate for Payment on Contract form:  Fill in required information.

- Mechanical and Electrical Specialty Trade Contractors’ draft monthly payment requests shall be submitted, for review and comment, prior to Owner’s review of the Design-Builder’s draft monthly Application for Payment.

- List Change Orders approved prior to the submission date individually (on the G703).  Use Owner's Cost Code designation and description (similar to an original component item of work). DO NOT BILL FOR CHANGE ORDER PROPOSALS UNTIL AN APPROVED CHANGE ORDER HAS BEEN RECEIVED FROM THE OWNER INCORPORATING THE PROPOSAL.

- Monthly Specialty Consultants/Specialty Trade Contractors List and Certifications form.

- Stored Materials:  The Design-Builder is solely responsible for the stored materials. Requests for payment on materials stored shall be for materials properly stored on the Project site.  Payment for materials stored off-site shall be at the sole option of the Owner and comply with conditions stipulated by the Owner.  These conditions may include, but are not limited to:

- Provide supplier invoice

b.	Provide insurance or a bond to cover the total loss of material and time impact to Project

- Monthly Project Schedule updates with change in Contract Time analysis.

- Apprentice and Journey Level Worker Utilization Report.

- Monthly Safety Report.

  - APPLICATION FOR PAYMENT

- On or before the tenth (10th) day of each month, beginning with the first month after the commencement, the Design-Builder shall submit to the Owner two (2) hardcopies of the Application for Payment for the Chargeable Costs of the Work properly performed during the previous calendar month to the Owner in accordance with this section and Article 7 of the Agreement.

- The Design-Builder is cautioned to carefully check all extensions, totals, and required information for accuracy before submittal.

- Applications are to be signed by a responsible officer of the Design-Builder.

- The Application for Payment shall include the following Owner forms and documents:

1.	Application and Certificate for Payment on Contract and G703

2.	Construction Invoice Voucher (for the total amount due)

3.	Retainage Invoice Voucher (for the retainage amount)

4.	Monthly Specialty Consultants/Specialty Trade Contractors List and Certifications

- Invoices for materials stored off-site

6.	Apprentice and Journey Level Worker Utilization Report

7.	Monthly Safety Report

- Contractor, subcontractor, or employer shall file a copy of its certified payroll records directly with the Department of Labor and Industries online system at least once per month.

- When the Owner’s Representative finds the Application for Payment properly completed and correct, they will sign and transmit all copies of the Application for Payment to the Capital Planning & Development Accounting Department for processing.

- If the Owner finds the Application for Payment improperly or incorrectly executed, an annotated copy will be returned for a new submittal.

- Only minor corrections are allowed on the original, with approval of Owner.

## 1.5    SUBCONTRACTOR PAYMENTS REPORTING REQUIREMENTS

### This Contract is subject to compliance tracking using the State’s business diversity management system, Access Equity (B2Gnow). Access Equity is web-based and can be accessed at the Office of Minority and Women’s Business Enterprises at https://omwbe.diversitycompliance.com/. The Contractor and all Subcontractors shall report and confirm receipt of payments made to the Contractor and each Subcontractor through Access Equity. For purposes of this requirement, Subcontractor means any subcontractor or subconsultant working on the Contract, at any tier and regardless of status as certified WMBE or Non-WMBE. The Contractor shall:

- Complete the required user training (two (2) one-hour online sessions) no later than 15 days after the Owner creates the Contract Record, if a new user.

- Register and enter all required Subcontractor information into Access Equity no later than 25 days after the Owner creates the Contract Record.

- Report the amount and date of all payments (i) received from the Owner, and (ii) paid to Subcontractors, no later than 15 days after issuance of each payment made by the Owner to the Contractor, unless otherwise specified in writing by the Owner, except that the Contractor shall mark as “Final” and report the final Subcontractor payment(s) into Access Equity no later than thirty (30) days after the final payment is due the Subcontractor(s) under the Contract, with all payment information entered no later than sixty (60) days after end of fiscal year.

- Monitor contract payments and respond promptly to any requests or instructions from the Owner or system-generated messages to check or provide information in Access Equity.

- Coordinate with Subcontractors, or Owner when necessary, to resolve promptly any discrepancies between reported and received payments.

- Respond to reasonable requests from the Owner for additional information to be provided electronically through Access Equity.

- Require each Subcontractor to: (a) register in Access Equity and complete the required user training; (b) verify the amount and date of receipt of each payment from the Contractor or a higher tier Subcontractor, if applicable, through Access Equity; (c) report payments made to any lower tier Subcontractors, if any, in the same manner as specified herein; (d) respond promptly to any requests or instructions from the Contractor or system-generated messages to check or provide information in Access Equity; and (e) coordinate with Contractor, or Owner when necessary, to resolve promptly any discrepancies between reported and received payments.

1.6    PRIOR TO FINAL APPLICATION FOR PAYMENT

A.	The final Application for Payment request will be accepted for processing only after providing satisfactory completion of the following:

1.	Application and Certificate for Payment on Contract and G703

2.	Construction Invoice Voucher (for the total amount due)

3.	Retainage Invoice Voucher (for the retainage amount)

4.	Monthly Specialty Consultants/Specialty Trade Contractors List and Certifications

5.	Invoices for materials stored off-site

6.	Final Completion procedures of the Agreement and Section 01 77 00 "Closeout Procedures"

- Final Schedule of Values "Final Actual Cost"

- Apprentice and Journey Level Worker Utilization Report

- Monthly Safety Report

1.7   RELEASE OF RETAINAGE

A.	Pursuant to the completion of Work performed in accordance with the Agreement and Final Acceptance by the Owner, the following requirements must be satisfied prior to the release of retained Contract funds.

1.	“Notice of Completion of Public Works Contract (REV 31 0020)”:  This Department of Revenue form will be completed by the Owner, establishing the date of Final Acceptance thereon.  Three copies of the notice will be mailed to the Department of Revenue and a copy will be transmitted to Design-Builder.

2.	“Certificate of Payment of State Excise Taxes by Public Works Design-Builder (REV 31 0028)”:  Following receipt of the Owner’s Notice of Completion of Public Works Contract form and after determining that all taxes, interest and penalties due from Design-Builder have been paid, the Department of Revenue will issue this certificate to Owner, thereby notifying the Owner that it has no objection to the release of retainage to the Design-Builder.

3.	“Certificate of Payment of Contributions, Penalties and Interest on Public Work Contract (EMS 8449 760)”:  Upon receiving a copy of the Owner’s Notice of Completion of Public Works Contract form from the Department of Revenue and determining that the Design-Builder is in compliance with the provisions of the Employment Security Act, the Employment Security Department will issue this certificate to Owner, thereby notifying the Owner that it has no objection to the release of retainage to the Design-Builder.

4.	Upon receiving a copy of the Owner’s Notice of Completion of Public Works Contract form and determining that the Design-Builder is in compliance with the provisions of Chapter 51 RCW for payment of industrial insurance premiums, the Department of Labor and Industries will issue a certificate for the Owner, thereby notifying the Owner that it has no objection to the release of retainage to the Design-Builder.  Note that the Notice of Completion cannot be sent to the Department of Labor and Industries until all Intents and Affidavits have been approved and are on file with the Department of Labor and Industries (see item 5 below).

5.	“Affidavit of Wages Paid on Public Works Contract” (F700-007-000):   An Affidavit of Wages Paid, for the Design-Builder, each Specialty Trade Contractor, and each sub-tier Specialty Trade Contractor, approved by the Industrial Statistician of the Department of Labor and Industries, must be on file with the Washington State Department of Labor and Industries.  Design-Builders and Specialty Trade Contractor may file the Affidavit of Wages Paid either on-line at the website link provided in Appendix A or by completing the forms manually.

6.	“Certificate of Payment of Labor and Materials”:  This Owner’s form shall be completed by the Design-Builder and returned to the Owner.  If the only exception to full payment to all Specialty Trade Contractors is retainage owed to Specialty Trade Contractors, the appropriate box on the form should be checked.

7.	Invoice Voucher:  If the retained funds are on deposit in Owner accounts, the Design-Builder shall prepare a Retainage Invoice Voucher for the total amount retained and submit to the Owner for payment.  If these funds have been placed in escrow at the direction of Design-Builder, no further invoice is required.

B.	Retainage will be paid by the Owner to the Design-Builder sixty (60) days following the published date of Final Acceptance, contingent upon the Design-Builder’s compliance with provisions of public works statutes and as stated above.  If there are either unpaid taxes or unsatisfied claims of lien against the retained percentage, disbursement of retainage funds will be made in accordance with State of Washington law.

C.	Address all transmittal of retainage documents to the Owner's Contracts Office at:  University of Washington, Project Delivery Group, Box 352205, Seattle, Washington, 98195 - 2205.

PART 2 - PRODUCTS (Not Used)

PART 3 - EXECUTION (Not Used)

END OF SECTION